## Plan
Plan
Requirement (ID) | Task ID | Task | Start (date) | End (date) | Estimate (days) | Who | Status | Remaining Work | Dependencies
SRS template dokument | T1 | SRS Template - poglavlje 1 | 2020-11-04 | 13/4/2020 | 2 | Dominik Martinović | Completed | 0
| T2 | SRS Template - poglavlje 2 | 2020-11-04 | 13/4/2020 | 2 | Kristijan Hodja | In progress | 0 | Raid, Cocain
| T3 | SRS Template - poglavlje 3 | 2020-11-04 | 13/4/2020 | 2 | Jurica Stanko | Completed | 0
| T4 | SRS Template - poglavlje 4 | 2020-11-04 | 13/4/2020 | 2 | Toni Čavara | Completed | 0
| T5 | SRS Template - poglavlje 5 | 2020-11-04 | 13/4/2020 | 2 | Vjeran Šeremešić | Completed | 0
| T6 | SRS Template - poglavlje 6 | 2020-11-04 | 13/4/2020 | 2 | Dominik Paulić | Completed | 0
Prioritized requirements list | T7 |  |  |  | 2 | Jurica Stanko | Completed | 0
Projektna dokumentacija | T10 | Poglavlje 1 i 2 | 13/4/2020 | 16/4/2020 | 3 | Vjeran Šeremešić | Completed | 0
| T11 | Poglavlje 3 i 4 | 14/4/2020 | 16/4/2020 | 3 | Toni Čavara | Completed | 0
| T12 | Poglavlje 5 i 6 | 13/4/2020 | 15/4/2020 | 2 | Jurica Stanko | Completed | 0
| T13 | Poglavlje 7 i 8 | 15/4/2020 | 18/4/2020 | 3 | Dominik Paulić | Completed | 0
| T14 | Poglavlje 9 i 10 | 13/4/2020 | 17/4/2020 | 4 | Dominik Martinović | Completed | 0